## Sprint Backlog F21 - T17
AGILE SPRINT BACKLOG F21 - T17
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1 | 100
Setup Datebase and Get Access to it |  | Jerish Bovas | Not Started | 16 | 0 | 0 | 0 | 0 | 0
Setup Classes to process info |  | Jerish Bovas | Not Started | 8 | 0 | 0 | 0 | 0 | 0
Design UI |  | Jerish Bovas | Not Started | 12 | 0 | 0 | 0 | 0 | 0
Test |  | Jerish Bovas | Not Started | 4 | 0 | 0 | 0 | 0 | 0
User Story #2 | 95
Setup FAQ Database and way to add info to it |  | Sanjay Kannan | Not Started | 8 | 0 | 0 | 0 | 0 | 0
Add info to Database |  | Sanjay Kannan | Not Started | 8 | 0 | 0 | 0 | 0 | 0
Setup Classes to process info |  | Sanjay Kannan | Not Started | 4 | 0 | 0 | 0 | 0 | 0
Test Code for efficiency |  | Sanjay Kannan | Not Started | 4 | 0 | 0 | 0 | 0 | 0
Design UI |  | Sanjay Kannan | Not Started | 12 | 0 | 0 | 0 | 0 | 0
Test Application |  | Sanjay Kannan | Not Started | 4 | 0 | 0 | 0 | 0 | 0
User Story #3 | 90
Use google services to understand meaning from keywords |  | Naveen Jose | Not Started | 16 | 0 | 0 | 0 | 0 | 0
Setup replying interface |  | Naveen Jose | Not Started | 16 | 0 | 0 | 0 | 0 | 0
Test app for working |  | Naveen Jose | Not Started | 4 | 0 | 0 | 0 | 0 | 0
Design UI |  | Naveen Jose | Not Started | 8 | 0 | 0 | 0 | 0 | 0
Test |  | Naveen Jose | Not Started | 4 | 0 | 0 | 0 | 0 | 0
User Story #4 | 87
Get info about Fees and charges from the company |  | Jesse Hughes | Not Started | 8 | 0 | 0 | 0 | 0 | 0
Design classes to proess query and calculate result |  | Jesse Hughes | Not Started | 8 | 0 | 0 | 0 | 0 | 0
Setup return result interface |  | Jesse Hughes | Not Started | 8 | 0 | 0 | 0 | 0 | 0
Design UI |  | Jesse Hughes | Not Started | 8 | 0 | 0 | 0 | 0 | 0
Test Application |  | Jesse Hughes | Not Started | 4 | 0 | 0 | 0 | 0 | 0
User Story #5 | 90
Setup some basic options to be asked with the help of consultant |  | Jerish Bovas | Not Started | 8 | 0 | 0 | 0 | 0 | 0
Design classes to show the info |  | Jerish Bovas | Not Started | 8 | 0 | 0 | 0 | 0 | 0
Design UI |  | Jerish Bovas | Not Started | 12 | 0 | 0 | 0 | 0 | 0
Test Application |  | Jerish Bovas | Not Started | 4 | 0 | 0 | 0 | 0 | 0
User Story #6 | 80
Use Servies to record how conversation is going |  | Sanjay kannan | Not Started | 12 | 0 | 0 | 0 | 0 | 0
set a way to contact to actual person |  | Sanjay kannan | Not Started | 4 | 0 | 0 | 0 | 0 | 0
setup classes and interfaces |  | Sanjay kannan | Not Started | 4 | 0 | 0 | 0 | 0 | 0
Test |  | Sanjay kannan | Not Started | 4 | 0 | 0 | 0 | 0 | 0
User Story #7 | 80
Setup a way to upload word doc to cloud |  | Naveen Jose | Not Started | 4 | 0 | 0 | 0 | 0 | 0
Design classes to process doc and enter them in database |  | Naveen Jose | Not Started | 8 | 0 | 0 | 0 | 0 | 0
Test |  | Naveen Jose | Not Started | 4 | 0 | 0 | 0 | 0 | 0
User Story #8 | 75
Train sample with more info |  | Jesse Hughes | Not Started | 16 | 0 | 0 | 0 | 0 | 0
collect more info for the system to process |  | Jesse Hughes | Not Started | 16 | 0 | 0 | 0 | 0 | 0
Use techniques from online |  | Jesse Hughes | Not Started | 8 | 0 | 0 | 0 | 0 | 0
Test |  | Jesse Hughes | Not Started | 8 | 0 | 0 | 0 | 0 | 0
User Story #9 | 75
Setup a way to greet user |  | Jerish Bovas | Not Started | 4 | 0 | 0 | 0 | 0 | 0
Test |  | Jerish Bovas | Not Started | 2 | 0 | 0 | 0 | 0 | 0
User Story #10 | 73
Get login APIs from social sites |  | Sanjay Kannan | Not Started | 4 | 0 | 0 | 0 | 0 | 0
Setup authentication methods and store user info from social sites |  | Sanjay Kannan | Not Started | 8 | 0 | 0 | 0 | 0 | 0
Implement classes and interfaces |  | Sanjay Kannan | Not Started | 8 | 0 | 0 | 0 | 0 | 0
Test |  | Sanjay Kannan | Not Started | 4 | 0 | 0 | 0 | 0 | 0
User Story #11 | 70
Setup database to store customer info |  | Naveen Jose | Not Started | 4 | 0 | 0 | 0 | 0 | 0
Implement classes and interfaces |  | Naveen Jose | Not Started | 4 | 0 | 0 | 0 | 0 | 0
Design UI |  | Naveen Jose | Not Started | 8 | 0 | 0 | 0 | 0 | 0
Test |  | Naveen Jose | Not Started | 4 | 0 | 0 | 0 | 0 | 0
User Story #12 | 68
Setup file store to store chat transcript |  | Jesse Hughes | Not Started | 4 | 0 | 0 | 0 | 0 | 0
implement classes to process transcript |  | Jesse Hughes | Not Started | 8 | 0 | 0 | 0 | 0 | 0
setup methods to send transcript to customers |  | Jesse Hughes | Not Started | 4 | 0 | 0 | 0 | 0 | 0
Test |  | Jesse Hughes | Not Started | 4 | 0 | 0 | 0 | 0 | 0
User Story #13 | 68
make form templates for survey, review and rating |  | Jerish Bovas | Not Started | 6 | 0 | 0 | 0 | 0 | 0
implement methods and storage ways |  | Jerish Bovas | Not Started | 8 | 0 | 0 | 0 | 0 | 0
Design UI |  | Jerish Bovas | Not Started | 10 | 0 | 0 | 0 | 0 | 0
Test |  | Jerish Bovas | Not Started | 4 | 0 | 0 | 0 | 0 | 0
User Story #14 | 60
get share APIs from social sites |  | Sanjay Kannan | Not Started | 4 | 0 | 0 | 0 | 0 | 0
Setup ways to connect sites |  | Sanjay Kannan | Not Started | 8 | 0 | 0 | 0 | 0 | 0
Desing share buttons |  | Sanjay Kannan | Not Started | 3 | 0 | 0 | 0 | 0 | 0
Test |  | Sanjay Kannan | Not Started | 4 | 0 | 0 | 0 | 0 | 0
User Story #15 | 55
Design different types of interface with different colors |  | Naveen Jose | Not Started | 16 | 0 | 0 | 0 | 0 | 0
Provide a way to give choice to users |  | Naveen Jose | Not Started | 4 | 0 | 0 | 0 | 0 | 0
Desing and implement classes |  | Naveen Jose | Not Started | 4 | 0 | 0 | 0 | 0 | 0
Test |  | Naveen Jose | Not Started | 4 | 0 | 0 | 0 | 0 | 0
User Story #16 | 50
setup database to store timestamp of chat |  | Jesse Hughes | Not Started | 2 | 0 | 0 | 0 | 0 | 0
classes to show timestamp |  | Jesse Hughes | Not Started | 2 | 0 | 0 | 0 | 0 | 0
methods to access timestamp when needed |  | Jesse Hughes | Not Started | 6 | 0 | 0 | 0 | 0 | 0
Test |  | Jesse Hughes | Not Started | 2 | 0 | 0 | 0 | 0 | 0
User Story #17 | 50
Setup fancy UI and other ideas to attract customers |  | Jerish Bovas | Not Started | 12 | 0 | 0 | 0 | 0 | 0
Test |  | Jerish Bovas | Not Started | 4 | 0 | 0 | 0 | 0 | 0
TOTAL |  |  |  | 457 | 0 | 0 | 0 | 0 | 0 | 0